## Title
Template Version 2.0
Internal Use Only
Document Revision History
| Version | Date | Author | Change Description | Reviewed By | Reviewed Date dd-mm-yyyy | Approved By | Approved Date dd-mm-yyyy
Template Revision History
| Version | Date | Author | Change Description | Reviewed By | Reviewed Date dd-mm-yyyy | Approved By | Approved Date dd-mm-yyyy
| 1.0 | 2018-05-25 | Sanjay Welling | New template | Amit S | 2018-05-26 | Sriniwas N | 2018-05-28
| 2.0 | 2019-06-06 | Neha Khatri | Converted to Teleperformance logo & format | Sanjay Welling | 2019-06-06 | Sriniwas Narayanan | 2019-06-06
Copyright © 2020 by Teleperformance.
Resource Register
Indian Energy Exchange Ltd.
Project Schedule
Teleperformance

## Project Schedule
Sr. No. | Task Name | Duration(Hrs) | Start | Finish | Predecessors | Resource Name
1 | Project Management
1.1 | Prepare the Project Plan
1.2 | Meetings with Client and stake holders
1.3 | Metrics Analysis
1.4 | Monitor the Project
2 | Requirement Development
2.1 | Requirement Elicitation & Gathering | NA
2.2 | SRS Preparation | NA
2.3 | SRS Review | NA
2.4 | SRS Sign Off | NA
3 | Infra Readiness at Client Side
3.1 | Server Configuration | NA
3.2 | Network Access to Users | NA
4 | Planning & Designing Phase
4.1 | Resource Allocation | 3 | 2021-08-06 | 2021-08-06 |  | Anil Kumar
5 | Development
5.1 | Upload Interface Flight Refund | 9.6 | 2021-08-09 | 2021-08-10 | 4.1 | Pawan Kumar
5.2 | Upload Interface Failed Voucher | 10.8 | 2021-08-10 | 2021-08-11 | 5.1 | Pawan Kumar
5.3 | Upload Interface OMOP | 10.8 | 2021-08-11 | 2021-08-12 | 5.2 | Pawan Kumar
5.4 | Assignment Automation - Logic to return Cases FIFO | 14.4 | 2021-08-13 | 2021-08-16 | 5.3 | Pawan Kumar
5.5 | WAT Model Develeopment Changes - New WAT Type Build | 14 | 2021-08-16 | 2021-08-18 | 5.4 | Pawan Kumar
5.6 | WAT Model Develeopment Changes - Dynamic Content - Configuration | 14.4 | 2021-08-19 | 2021-08-20 | 5.5 | Pawan Kumar
5.7 | WAT Model Develeopment Changes - Dynamic Content - Display | 14.4 | 2021-08-20 | 2021-08-24 | 5.6 | Pawan Kumar
5.8 | WAT Model Develeopment Changes - Case Fetch Implementation | 14.4 | 2021-08-24 | 2021-08-26 | 5.7 | Pawan Kumar
5.9 | WAT Model Develeopment Changes - Disposition Screen Autofill | 14.4 | 2021-08-26 | 2021-08-30 | 5.8 | Pawan Kumar
5.10 | WAT Model Develeopment Changes - Disposition Screen Autofill - Configuration | 14.4 | 2021-08-30 | 2021-09-01 | 5.9 | Pawan Kumar
5.11 | WAT Model Develeopment Changes - Provision to auto fetch next case / no case | 19.2 | 2021-09-01 | 2021-09-03 | 5.10 | Pawan Kumar
5.12 | WAT Model Develeopment Changes - Activity Time Consolidation | 12 | 2021-09-06 | 2021-09-07 | 5.11 | Pawan Kumar
5.13 | WAT Model Develeopment Changes - Other code changes for other types | 14.4 | 2021-09-07 | 2021-09-09 | 5.12 | Pawan Kumar
5.14 | WAT Model Configuration -Configure WAT for Flight Refund | 6 | 2021-09-09 | 2021-09-09 | 5.13 | Pawan Kumar
5.15 | WAT Model Configuration -Configure WAT for Failed Voucher | 6 | 2021-09-10 | 2021-09-10 | 5.14 | Pawan Kumar
5.16 | WAT Model Configuration -Configure WAT for OMOP | 6 | 2021-09-10 | 2021-09-13 | 5.15 | Pawan Kumar
5.17 | Reports - New Report | 21.6 | 2021-08-25 | 2021-08-27 |  | Mahesh Mamgain
5.18 | Reports - Live TM Canvas display | 43.2 | 2021-08-30 | 2021-09-03 | 5.17 | Mahesh Mamgain
5.19 | Reports - Live Dashboard Filters , Design & Misc | 32 | 2021-09-06 | 2021-09-09 | 5.18 | Mahesh Mamgain
6 | Unit Test
6.1 | Unit Test cases creation | 8 | 2021-09-10 | 2021-09-10 |  | Pawan Kumar
6.2 | Unit Test case Review | 5 | 2021-09-13 | 2021-09-13 | 6.1 | Mahesh Mamgain
6.3 | Unit Testing | 43 | 2021-09-13 | 2021-09-17 | 5.19,5.16 | Pawan Kumar
6.4 | Unit Test case Sign off | 1 | 2021-09-18 | 2021-09-18 | 6.3 | Anil Kumar
7 | Testing
7.1 | System Test Case Creation | 0
7.2 | System Test Case Review | 0
7.3 | System testing | 0
7.4 | System test case Signoff | 0
8 | Bugs Fixing
8.1 | Bugs Analysis | 4
8.2 | Module Bug Fixing | 12
9 | Deployment
9.1 | UAT | 16 | 2021-09-20 | 2021-09-21 | 6.4 | Ops
9.2 | UAT Fixes | 12 | 2021-09-22 | 2021-09-23 | 9.1 | Pawan Kumar & Mahesh
9.3 | RE UAT | 8 | 2021-09-24 | 2021-09-24 | 9.2 | Ops
9.4 | UAT Sign Off | 4 | 2021-09-24 | 2021-09-24 | 9.3 | Ops
9.5 | Production Deployment | 16 | 2021-09-25 | 2021-09-26 | 9.3 | Mahesh Mamgain
9.6 | Go Live | 3 | 2021-09-26 | 2021-09-26 | 9.3 | Ops
Formulas:
Finish = [Start]
Finish = [Start]+1
Start = [Finish, row above]
Start = [Finish, row above]+1

## Sheet1
| Start Date | End Date
Development | 2021-08-09 | 2021-09-13
Unit Testing | 2021-09-13 | 2021-09-13
UAT | 2021-09-20 | 2021-09-24
Go Live | 2021-09-25 | 2021-09-26